## Sheet1
Index | Party | Category | Comment | EHP comment response | PD updated in response?
1 | GPN and VNPA | Grassland | • The clearing of critically endangered grassland should not be allowed. Critically Endangered grassland too rare to clear and offset: The grassland at 103 Reid Street and 18B Jonesfield Corner are part of a connected system supporting local biodiversity, including Striped Legless Lizard and Growling Grass Frog, several EPBC-listed plant species such as Spiny Rice-flower, as well as FFG-listed species such as Tussock Skink. Other grasslands exist directly opposite along Jones Creek. Further grasslands are present nearby (Figure 1). These all support each other. To clear the Jonesfield Corner Grassland is to have direct impacts on all these adjacent patches of biodiversity. It will reduce options for landscape-wide conservation. Overall, the long-term viability of the other remnants in Cairnlea and nearby will decline. Isolated native grasslands have less buffering capacity and resilience to environmental change relative to more connected native grasslands. | The PD has been updated to include further discussion and review of broader impacts to the partially connected system of grasslands and resident flora and fauna. | Yes - Section 3.3.3, 4.4.3
2 | GPN and VNPA | General | • The proponent’s documentation is premature, incomplete, and wastes government and stakeholders’ time. | Unable to respond as the comment does not provide examples to support these claims. | No.
3 | GPN and VNPA | Rezoning | • The proposal relies on a road connection that is yet to be determined: The development masterplan is predicated on a road connection that currently does not, and may never, exist. The proposed road connection is dependent on the resolution of the still-to-be-determined Cairnlea Section G Mixed Use Development, EPBC 2020/8720. No evidence is provided of any investigation into options for a road connection (Figure 2). | This is a Council and/or State planning issue. Not relevant to this documentation and Commonwealth assessment. | No.
4 | GPN and VNPA | Rezoning | • The proposal requires rezoning, which is far from certain: The proposed road connection is dependent on the resolution of the still-to-be-determined Cairnlea Section G Mixed Use Development, EPBC 2020/8720. | This is a Council and/or State planning issue. Not relevant to this documentation and Commonwealth assessment. | No.
5 | GPN and VNPA | Rezoning / Masterplan | • The proposal fails to meet basic City of Brimbank planning criteria. The masterplan presented would not meet local planning requirements. It requires rezoning, provides no WSUD or public open space, and has inadequate setback from the Jones Creek top of bank. | This is a Council and/or State planning issue. Not relevant to this documentation and Commonwealth assessment. However, a 30 metre setback has now been applied to Jones Creek, avoiding impacts to 1.07ha of SLL habitat and 0.08ha of NTGVVP. | Yes - throughout
6 | GPN and VNPA | Survey methodology | • The proposal does not provide basic information around methodologies used in the Fauna and flora Assessment: The preliminary documentation provides inadequate detail around flora and fauna assessment methods. No independent analysis can be undertaken without this data. | Minor updates made to Section 3 of PD. Requested information already largely provided. | Yes - Section 3
7 | GPN and VNPA | Jones Creek Corridor | • Any development should retain grassland and biodiversity corridor along Jones Creek: At the very least, a 100 meter setback should be retained along Jones Creek, and a link east to the Denton Avenue landfill future restoration site and Denton Avenue Grassland ensured (Figure 3). | A 30 metre setback has now been applied to Jones Creek, avoiding impacts to 1.07ha of SLL habitat and 0.08ha of NTGVVP. | Yes - throughout
8 | GPN and VNPA | Section 173 | • The proposed land use at 103 Reid Street is difficult to understand and requires clarification. For instance, 1.4 ha seems to have been omitted from offsetting calculations. No discussion is presented around existing on-title agreements. Currently the proposal is open to misunderstanding. | There appears to be some confusion that the southern portion of 103 Reid Street (i.e. southern site) is proposed to be impacted. This is not the case. The PD notes throughout that the Southern Site is proposed for on-site offsets (see Section 6.1.1; Figure 2a; Figure 2b), while the Northern Site is proposed to be developed as part of the proposed action. The PD has been updated to further clarify that the southern portion of 103 Reid Street is proposed to contain an on-site offset site and will not be impacted as part of the proposed action. | Yes - Section 1
9 | GPN and VNPA | GGF | • The site is an important overwintering and foraging location for a known nearby population of endangered growling grass frogs. This has not been taken into consideration: Kororoit Creek and its tributary Jones Creek has a known metapopulation of Growling Grass Frog. The project location should be considered an important overwintering and foraging location for this species. Appropriate surveys need to be undertaken. | Online databases (ALA 2025, DEECA 2025, iNaturalist 2025) were reviewed for published records of Growling Grass Frog Litoria raniformis major (GGF) in the vicinity of the Development Site. No published records of GGF within Jones Creek were identified. Suitable habitat for GGF is absent from the portion of Jones Creek adjacent to the Development Site; this section comprises a concrete lined drain with none of the habitat characteristics preferred by GGF, such as floating and emergent vegetation and large pools of deep water. Suitable habitat may be present along Jones Creek and in the ponds within the Kevin Flint Memorial Reserve approximately 500 metres north of the Development Site, however, there are no published records of GGF within this area. There is a known population of GGF within Kororoit Creek, primarily occurring within Caroline Springs. A smaller population of GGF has previously been recorded in Deer Park, within constructed waterbodies adjacent to Kororoit Creek in 2004. Dispersal from these constructed waterbodies would be approximately two kilometres to the Development Site. GGF may be present within Kororoit Creek further south of these records, however, there have been no published observation of GGF within Kororoit Creek, south of the development area, within the past 20 years. According to Heard et al. (2010), the most important terrestrial habitat for Growling Grass Frog is land up to a distance of approximately 100 metres from the normal water level of aquatic habitat. Areas of potential but unconfirmed GGF aquatic habitat within Jones Creek and Koroit Creek are located further than 100 metres from the Development Site, and therefore the proposed action is unlikely to impact this species. ALA 2025. Atlas of Living Australia. URL: https://www.ala.org.au/ Heard, G. W. 2010. Pattern, process and the conservation of threatened amphibian metapopulations. PhD Dissertation, La Trobe University, Bundoora, Victoria, Australia. | No.
10 | GPN and VNPA | VGED | • Victorian Grassland Earless Dragon not appropriately considered: Careful consideration should be given to any assumptions about appropriate levels of cover, floristics, soil cracking and rock presence for Victorian Grassland Earless Dragon so as to not exclude areas that may well be suitable habitat. The project should not be allowed to proceed without the oversight of the Victorian Grassland Earless Dragon National Recovery Team. | The Victorian Grassland Earless Dragon (VGED) Tympanocryptis pinguicolla is listed as critically endangered under the EPBC Act and was previously thought to be extinct in Victoria until being rediscovered in 2023. A habitat assessment was conducted for the species in December 2025. Further information is now provided within the PD. | Yes.
11 | GPN and VNPA | Permit conditions | • Any permit ultimately provided should require: o All planting to support local grassland and riparian systems o Quality interpretive signage for all protected grassland o Improvement to the grassland condition in the interface area between the Reid Street fence and the shared path o Restoration of the scar cut through Reid Street Grassland o An active restoration program, with appropriate monitoring, and mechanisms to ensure the quality of the protected grasslands improves as measured by multiple KPIs, including floristic diversity, insect biomass, and weed cover o Any grassland not part of an offset should also have funding guaranteed for its proper management o The proponent should provide a community engagement plan to promote grassland values | Updated PD to include provision for planting of native specimens and grassland restoration in areas not impacted (i.e. adjacent to Jones Creek) and within the development site in proposed green spaces. Details for any restoration will be provided in the updated development plan for assessment by Brimbank | Yes
12 | GPN and VNPA | Public consultation process | • The consultation process should continue to include stakeholders such as those who have responded to this preliminary documentation. o Our understanding is that the proponent is required to summarise stakeholder responses (usually through a table) and provide their own comments regarding those responses, and to then provide the summary table to DEECCW. o We request to receive a copy of that summary table (or its equivalent) to ensure that our submission has been correctly summarised and understood. In our experience this provision of the summary table to stakeholders such as ourselves does not automatically occur, hence we are including this request here and in our correspondence to Ecology and Heritage Partners, as well as directly to DCCEEW. | Noted - provided. | No.
13 | GPN and VNPA | Community benefits | • Retaining grassland comes with social and well-being benefits: an opportunity for more thoughtful development The grassland patches at Reid Street and Jonesfield Corner should be integrated into an urban design solution that protects remnant vegetation and provides substantial community benefit. | Updated PD to include provision for planting of native specimens and grassland restoration in areas not impacted (i.e. adjacent to Jones Creek) and within the development site in proposed green spaces. Details for any restoration will be provided in the updated development plan for assessment by Brimbank | Yes
14 | GPN and VNPA | SLL / Translocation | • Salvage of Striped Legless Lizard for research purposes The proposal should not allow the destruction of critically endangered Striped Legless Lizards. It is entirely possible to translocate these creatures, and salvage and translocation is permissible for research purposes. Policy restricting salvage and location was developed because insufficient research had been done to show that translocation and salvage could be successful. There has not been a substantial body of research since to interrogate this matter. Any development should also fund research to better understand the potential for translocation. That way, the loss of this population can at least have good research outcomes. Crushing protected species under a bulldozer is inappropriate, and flies in the face of community concern. | The effectiveness of salvage and translocation for Striped Legless Lizard has been investigated as recommended in the species National Recovery Plan (O’Shea 2013); seven fundamental criteria for selecting a suitable recipient site are outlined, and it was recommended that translocated populations have a minimum of 75 individuals and are translocated to a site of at least 35 hectares of grassland habitat with no Striped Legless Lizard populations within one kilometre. A total of 16 SLL has been recorded during a single survey season within the Development Site; considering the species can be cryptic and difficult to observe, and their tendency to be trap shy, it is possible that the Striped Legless Lizard population is large enough to provide sufficient specimens to establish a new population in the local area. In situ management for Striped Legless Lizard is always the preferred approach for the conservation of the species, and salvage and relocation of Striped Legless Lizard is not a suitable compensation or in any way mitigates the loss of habitat for the species (DSE 2010; Clemann et. al. 2025). Regardless, providing a suitable recipient site that meets the seven fundamental criteria (O’Shea 2023) is identified, it is recommended that a Salvage and Translocation Plan for any Striped Legless Lizard individuals, or other threatened reptiles such as Tussock Skink Pseudemoia pagenstecheri, encountered during the early earthworks within the Development Site is prepared to reduce the mortality of Striped Legless Lizard directly related to the development. A Salvage and Translocation Plan would be prepared in consultation with a herpetologist with extensive experience and understanding of the ecology of Striped Legless Lizard. While this does not mitigate the loss of important grassland habitat, it may provide a research opportunity to fill in knowledge gaps of the species and establish a new Striped Legless Lizard population in a suitable location. | Yes - Section 4.3.3, 6.1.1
15 | GPN and VNPA | Tussock Skink | • Tussock Skink: Tussock Skink are present. These are listed as Vulnerable in Victoria. Efforts should be made to protect these species. | The PD does not consider matters that are not Commonwealth MNES. Potential impacts to Tussock Skink are addressed within the planning permit application | No.
16 | Megan O'Shea | Spiny Rice-flower | • At 103 Reid Street, the number of Spiny Rice-flower plants has increased in number and their distribution has expanded over the lifespan of the project proposal. This indicates that despite a lack of management, the site is able to support positive population growth of this critically endangered species – a trajectory that may also be applicable to some of the other native herbaceous species at the site. Positive population growth has not been widely documented for Spiny Rice-flower populations, giving this site particular significance for the species. | Correct. There appears to be some confusion that the southern portion of 103 Reid Street (i.e. southern site) is proposed to be impacted. This is not the case. The PD notes throughout that the Southern Site is proposed for on-site offsets (see Section 6.1.1; Figure 2a; Figure 2b), while the Northern Site is proposed to be developed as part of the proposed action. The PD has been updated to further clarify that the southern portion of 103 Reid Street is proposed to contain an on-site offset site and will not be impacted as part of the proposed action. | Yes - Section 1
17 | Megan O'Shea | Spiny Rice-flower | • There are 38 sites in the Brimbank City Council LGA that support Spiny Rice-flower. This site is one of only four that support more than 100 individuals – it is clearly a significant site for this species within the municipality. Genetic material from this 103 Reid Street could make important contributions to the recovery efforts for other populations of the species within Brimbank (and further afield). | Correct. There appears to be some confusion that the southern portion of 103 Reid Street (i.e. southern site) is proposed to be impacted. This is not the case. The PD notes throughout that the Southern Site is proposed for on-site offsets (see Section 6.1.1; Figure 2a; Figure 2b), while the Northern Site is proposed to be developed as part of the proposed action. The PD has been updated to further clarify that the southern portion of 103 Reid Street is proposed to contain an on-site offset site and will not be impacted as part of the proposed action. | Yes - Section 1
18 | Megan O'Shea | Striped Legless Lizard | • Both 103 Reid Street and 18b Jonesfield Corner support important populations of Striped Legless Lizard Delma impar | Agreed. This is already discussed within the PD. | No.
19 | Megan O'Shea | Striped Legless Lizard | • Both sites make significant contributions to the Jones Creek Grassland Corridor which supports a metapopulation of the species and should therefore be retained in their entirety to support long-term viability of the overall population. | The PD has been updated to include further discussion and review of broader impacts to the partially connected system of grasslands and resident flora and fauna. A 30 metre setback has now been applied to Jones Creek, avoiding impacts to 1.07ha of SLL habitat and 0.08ha of NTGVVP. | Yes - Section 3.3.3, 4.4.3
20 | Megan O'Shea | Striped Legless Lizard | • Various components of the Jones Creek metapopulation have been intensively studied at various points in time, including Iramoo Wildflower Grassland Reserve, Victoria University Grassland and Denton Avenue Grassland. Surveys have also been done at Howardson Circuit Grassland, Pimelea Wildflower Grassland and along the banks of Jones Creek, where the species was detected. Thus, the sites referred to in the application are part of a metapopulation for which various components have been documented over a long period of time, collectively making them valuable in terms of data relating to the conservation of the species. | The PD has been updated to include further discussion and review of broader impacts to the partially connected system of grasslands and resident flora and fauna, including the SLL meta-population. A 30 metre setback has now been applied to Jones Creek, avoiding impacts to 1.07ha of SLL habitat and 0.08ha of NTGVVP. | Yes - Section 3.3.3, 4.4.3
21 | Megan O'Shea | Striped Legless Lizard | • The detection of 16 Striped Legless Lizards across three roof tile grids (and within a single survey season) at 18b Jonesfield Corner suggests that the population at this site is of considerable size, and is likely to support a reproductively active population that is helping to ensure the long-term viability of the Jones Creek metapopulation. | Agreed. Further detail on the significance of this population in the context of the meta-population has been provided in the PD. | Yes - Section 3.3.3, 4.4.3
22 | Megan O'Shea | Striped Legless Lizard | • Striped Legless Lizards are known to occupy grassy habitat that is dominated by exotic vegetation – I agree that the entirety of both sites should be considered habitat. | Noted. | No.
23 | Megan O'Shea | Striped Legless Lizard / Offsets | • I have not looked at the information provided for the offsite offsets but it concerns me that ‘area of habitat’ is used as a measure for settling Striped Legless Lizard offsets when potentially very little is known about the size of the populations at either of the development or offset sites. Does area of habitat represent a true equivalence? | Offsets do not only draw on area of habitat. Stocking rate, habitat quality, and site context are also factors - these factors are already considered in Section XX of the PD. | No.
24 | Megan O'Shea | Striped Legless Lizard / Translocation | • Noting that I do not support clearance of any Stiped Legless Lizard habitat for the proposed project, if habitat is to be destroyed then a fully developed salvage and translocation project should be undertaken in order to bolster local populations. The Tussock Skink Pseudemoia pagenstecheri should also be included if such an action is to occur. | The effectiveness of salvage and translocation for Striped Legless Lizard has been investigated as recommended in the species National Recovery Plan (O’Shea 2013); seven fundamental criteria for selecting a suitable recipient site are outlined, and it was recommended that translocated populations have a minimum of 75 individuals and are translocated to a site of at least 35 hectares of grassland habitat with no Striped Legless Lizard populations within one kilometre. A total of 16 SLL has been recorded during a single survey season within the Development Site; considering the species can be cryptic and difficult to observe, and their tendency to be trap shy, it is possible that the Striped Legless Lizard population is large enough to provide sufficient specimens to establish a new population in the local area. In situ management for Striped Legless Lizard is always the preferred approach for the conservation of the species, and salvage and relocation of Striped Legless Lizard is not a suitable compensation or in any way mitigates the loss of habitat for the species (DSE 2010; Clemann et. al. 2025). Regardless, providing a suitable recipient site that meets the seven fundamental criteria (O’Shea 2023) is identified, it is recommended that a Salvage and Translocation Plan for any Striped Legless Lizard individuals, or other threatened reptiles such as Tussock Skink Pseudemoia pagenstecheri, encountered during the early earthworks within the Development Site is prepared to reduce the mortality of Striped Legless Lizard directly related to the development. A Salvage and Translocation Plan would be prepared in consultation with a herpetologist with extensive experience and understanding of the ecology of Striped Legless Lizard. While this does not mitigate the loss of important grassland habitat, it may provide a research opportunity to fill in knowledge gaps of the species and establish a new Striped Legless Lizard population in a suitable location. | Yes - Section 4.3.3, 6.1.1
25 | Megan O'Shea | Striped Legless Lizard | • I believe that many more than 99 (as claimed on page 16) individual Striped Legless Lizards were unearthed during the development of the Cairnlea Estate (refer to the report by Timewell & Kimber for detailed documentation). From memory, the number was several hundred, again indicating the importance of Cairnlea and the Jones Creek Corridor for this species. | Thanks for noting this. 99 SLL were unearthed during excavation for roads and services. This section of the PD has been updated to reflect that a further unknown number were unearthed during excavation for housing. | Yes - Section 3.3.3
26 | Megan O'Shea | Striped Legless Lizard | • It should be assumed that the small remnant grassland at the Cairnlea Estate development (colloquially referred to as the ‘Section G grassland’) supports Striped Legless Lizards and that these animals are part of the same population as those at 18b Jonesfield Corner. Development at Jonesfield Corner will isolate the remnant vegetation at ‘Section G’. | Thanks for highlighting this. The SLL existing conditions and proposed impact sections have been updated to reflect this. | Yes - Section 3.3.3, 4.4.3
27 | Megan O'Shea | 18b Jonesfield Corner | • Despite having considerable weeds, the sites support a good diversity and abundance of native herbaceous plants. There are large patches of Grassland Candles Stackhousia subterranea (which occur in only a few small patches at a couple of other sites within the area) and also good numbers of Curved Rice-flower Pimelea curviflora. Other species include Small St Johns Wort Hypericum gramineum, Wiry Dock Rumex dumosus, Emu Foot Cullen tenax and large patches of Tufted Bluebells Wahlenbergia. I observed many of these species following a burn which occurred at the site in the early 2020’s. Clearly the site has elements of a herb-rich grassland, despite the weeds. | Agreed. We have provided further detail in the PD to illustrate the underlying quality of the grassland despite weed presence. | Yes - Section 3.3.1
28 | Megan O'Shea | 18b Jonesfield Corner | • From experience managing other grassland sites in Cairnlea, we have found that some of our very weedy-looking sites can support a high level of native forb diversity that eludes detection. At the nearby Featherheads Wildflower Grassland, we found a population of over 90 Sun Orchids Thelymitra sp. following careful control of the abundant Serrated Tussock Nassella trichotoma. It is likely that a greater diversity of herbaceous flora would be detected at 18b Jonesfield Corner if the vegetation was appropriately managed. | Agreed. We have provided further detail in the PD to illustrate the underlying quality of the grassland despite weed presence. | Yes - Section 3.3.1
29 | Megan O'Shea | 18b Jonesfield Corner | • Furthermore, our restoration work at Featherheads and other local grasslands demonstrates that these areas can be restored (sometimes rapidly) because despite the weediness, they have not been subjected to significant physical disturbances such as cropping and rock removal. Jonesfield Corner represents a relatively in-tact site that has a weed management problem – underneath the weeds it has the capacity to function as remnant native grassland. | Agreed. We have provided further detail in the PD to illustrate the underlying quality of the grassland despite weed presence. | Yes - Section 3.3.1
30 | Megan O'Shea | 18b Jonesfield Corner | • Page 13 of the Preliminary Documentation refers to historic livestock grazing, as well as current cropping and intense grazing activities on surrounding properties – none of these are an accurate reflection of activities on or near the property. | Historical land use context is important background information noting that current site activities do not include livestock grazing. Any references to current cropping and grazing on nearby properties have been removed. | Yes - throughout
31 | Megan O'Shea | 18b Jonesfield Corner | • This site is landlocked – it is unclear how the site will be accessed without the destruction of habitat on nearby properties. Will approval at 18b Jonesfield Corner be the impetus for habitat clearance at ‘Section G’, and vice versa. How is this accounted for in the EPBC process? | Any future removal of habitat in the adjacent Development Victoria site is not considered in this assessment as the proposed action on the DV site has not received EPBC Act approval. The EPBC Act referral for the DV land lapsed in 2022. Any future referral on the DV site will need to consider the cumulative impacts associated with removal of habitat at 18b Jonesfield (if approved). | No.
32 | Megan O'Shea | Offsite Offsets | • The Brimbank and Cairnlea community cares about our local environment. We want our remnant native habitat to be protected and properly managed. We value our open spaces, especially when they provide habitat for our local iconic plants and animals. We want to be able to refer to the grasslands that once covered the area that we call home – indeed, we need to be able to see nature around us in order to value it. | Thank you. The PD is updated to include provision for planting of native specimens and grassland restoration in areas not impacted (i.e. adjacent to Jones Creek) and within the development site in proposed green spaces. Details for any restoration will be provided in the updated development plan for assessment by Brimbank | Yes - Section 6.3
33 | Megan O'Shea | Offsite Offsets | • I am concerned that offsets for our local remnant native vegetation are being created in places that most Brimbank residents will never see or hear about. Noting that I am opposed to the destruction of habitat and vegetation proposed in this project, any arising offsets should be acquired locally for the people living in Brimbank. | Efforts have been made to establish offsets in the local Brimbank community as part of this project. The on-site offset site is proposed for 103 Reid Street, Ardeer, immediately south of the development site.
34 | Brimbank City Council | Section 173 | There is an under estimation of impacts to NTGVVP of approx. 1 hectare and likely impacts to SLL habitat of approx. 1.5ha hectares. These impacts in the portion of the southern section of 103 Reid Street that is subject to a s173 agreement. The data relating to approx. half of the s173 agreement area is ‘missing’ from the document. | There appears to be some confusion that the southern portion of 103 Reid Street (i.e. southern site) is proposed to be impacted. This is not the case. The PD notes throughout that the Southern Site is proposed for on-site offsets (see Section 6.1.1; Figure 2a; Figure 2b), while the Northern Site is proposed to be developed as part of the proposed action. The PD has been updated to further clarify that the portion of 103 Reid Street south of the freeway is proposed to contain an on-site offset site and will not be impacted as part of the proposed action. | Yes - Section 1
35 | Brimbank City Council | Rezoning | The documentation is inaccurate with regards to the current status of the application to re-zone the land. | The rezoning application is still technically active, however an RFI has not yet been addressed by the proponent. | No.
36 | Brimbank City Council | Jones Creek Corridor | The Cairnlea/St Albans meta-population of Striped Legless Lizards and the current existing habitat connectivity corridor along the Jones Creek corridor is not addressed: a. Potential permanent impacts to the portion of this habitat connectivity corridor that occurs within the northern section of 103 Reid Street is not discussed. b. This is an omission of a large, permanent impact that would have on-going impacts on an MNES within the area. | The PD has been updated to include further discussion and review of broader impacts to the partially connected system of grasslands and resident flora and fauna. | Yes - Section 3.3.3, 4.4.3
37 | Brimbank City Council | Onsite Offsets | There is no detailed mapping of the land parcels provided and the location of the parcel ‘57A Reid Street’ cannot be located- even though it is stated that this parcel is part of the on-site offset zone. | Mapping updates undertaken to address this gap. | Yes - Figure 2a, 2b
38 | Brimbank City Council | Mapping | Comment 1 – inadequate maps/plans in the response: There is no map within the document that clearly identifies each of the three land parcels. From our internal mapping we have the following information as copied in the figure on the next page - however we cannot determine, which section of the proposal is 57 and 57A Reid Street- this area is currently subject to a subdivision application, and neither our internal system or VicPlan depict which section is 57A Reid Street. | Mapping updates undertaken to address this gap. Can clarify that 57a Reid Street is not within the Development Site or On-site Offset Site and mention of this property has been removed from the PD. | Yes - Figure 2a, 2b
39 | Brimbank City Council | ESO | The response also does not discuss the Environmental Significance Overlay – Schedule 6 (ESO6) which covers the entire site. | The PD does not consider matters that are not Commonwealth MNES. ESO implication are addressed within the planning permit application. | No.
40 | Brimbank City Council | Mapping | Comment 2- Inaccurate mapping or inaccurate site description: Figure 2A in the EPBC document depicts the study area as covering these land parcels- according to VicPlan- these land parcels do not encompass 57 Reid Street. Our figures provided above depict the land parcel known as 57 Reid Street. | Mapping updates undertaken to address this gap. | Yes - Figure 2a, 2b
41 | Brimbank City Council | Section 173 | Comment 3 – inadequate description of activities associated with the subdivision of the land: DCCEEWs request for Preliminary Documentation included as copied above- that the detailed description of the proposed action must include a description of the activities associated with the subdivision of the land. No mention is made of the section 173 (s173) agreement that covers the land and outlines the requirements for any proposed future development of the land subject to the s173 agreement- primarily the southern portion of 103 Reid Street. The s173 agreement is not mentioned until Section 7.3, Section 9 and Appendix 2. This is despite the subject site clearly encompassing the area subject to the s173 agreement. The map of the s173 agreement affected area is copied below- this map clearly depicts that the majority of the southern portion of 103 Reid Street (approx. 3.6ha) is subject to the terms of the s173 agreement. | There appears to be some confusion that the southern portion of 103 Reid Street (i.e. southern site) is proposed to be impacted. This is not the case. The PD notes throughout that the Southern Site is proposed for on-site offsets (see Section 6.1.1; Figure 2a; Figure 2b), while the Northern Site is proposed to be developed as part of the proposed action. The PD has been updated to further clarify that the portion of 103 Reid Street south of the freeway is proposed to contain an on-site offset site and will not be impacted as part of the proposed action. | Yes - Section 1
42 | Brimbank City Council | Description of MNES | Section 3 – EPBC RFI Issue 2: Description of the Environment and MNES. Comment 1 – NO accompanying documents. The referral has not provided any of the documents that are listed as being the resources that have utilised to summarise the information provided in this section. Therefore, there is no way of verifying the information summarised in the document. | The information provided in the PD is sufficient. Reports authored by Ecology and Heritage Partners that are referenced within the PD were reviewed by Brimbank Council and finalised at the time of their preparation. | No.
43 | Brimbank City Council | Description of MNES | Comment 2 – advice sought from fauna experts: Brimbank is home to one of the State’s leading experts on Striped legless Lizards- Dr Megan O’Shea. Dr Megan O’Shea works at Victorian University and is heavily involved in the management of the Iramoo Grasslands Reserve, both sites that are connected to the subject site via Jones Creek and patchwork of conservation reserves and open space sites located along and/or connected to the Jones Creek corridor. Dr O’Shea was not approached for advice by the project consultants, despite the EPBC RFI requirement copied above. | Relevant fauna experts were contacted at multiple stages since the project was initially referred in 2014.
44 | Brimbank City Council | Description of MNES | Comment 3- SLL meta-population and significance of SLL population in the Cairnlea/St Albans Area: The Brimbank Env Dept recently reviewed project reports submitted for the remediation of the northern portion of 103 Reid Street. These reports discussed the SLL meta-population that occurred in the local area. It is interesting to note that this EPBC RFI report, that has been prepared by the same consultants, does not discuss the SLL meta-population and that any impact will be impacting the SLL meta-population within the local area. This EPBC RFI report, also does not discuss the habitat connectivity provided by the site, or it’s vital location with regards to the landscape link it provides between the Sunbury rail line/Denton Grasslands to the west of the site and the other known SLL sites located to the north of the site along the Jones Creek corridor. Due to the inadequacy of the information provided in this section of the report with regards to the known SLL meta-population that occurs along the Jones Creek corridor, we have re-copied our corridor connectivity image below, to illustrate the key location that the northern portion of 103 Reid Street has within the SLL St Albans/Cairnlea meta-population corridor. | The PD has been updated to include further discussion and review of broader impacts to the partially connected system of grasslands and resident flora and fauna, including the SLL meta-population. A 30 metre setback has now been applied to Jones Creek, avoiding impacts to 1.07ha of SLL habitat and 0.08ha of NTGVVP. | Yes - Section 3.3.3, 4.4.3
45 | Brimbank City Council | Description of MNES | Comment 4- Survey Timing (NTGVVP, SRF & SLL Surveys): The survey timing of the numerous surveys undertaken across the sites is listed throughout the document section for the three MNES. The briefest review of the dates reveals that many of the surveys were undertaken at either end of the stated survey time periods- in what reads to be sub-optimal survey periods. However, without detailed climatic/seasonal information provided for each survey date- was the survey year/month having above/below average rainfall? In a La Nina or El Nino weather cycle? In drought? Etc.. the dates listed are just dates. They do not provide any really useful information, without accompanying climatic/seasonal contextual information. NTGVVP is a highly climatically responsive vegetation type- a wet or dry year survey can yield highly variable survey results in the extent of native versus exotic grass cover. Rainfall and temperate also affect the growth/detection of seasonally herbaceous species and orchids/lilies. The same is also applicable to the flowering, and hence detection, of Spiny Rice-flowers. All plants are affected by seasonal/climatic influences. Whilst less is known about the influences of climate/seasons on SLLs- it is highly likely they are also subject to seasonal/climatic influences. This section needs to include information on the limitations of ecological surveys and that they are point in time surveys that are utilised as an indication of what may be present in a site- they do not provide compete information on a site, they are just an indication of a site’s ecological values. | Updates undertaken to Section 3 of PD, including regarding climate. | Yes - Section 3
46 | Brimbank City Council | NTGVVP | Section 4 – EPBC RFI Issue 3: Relevant Impacts. Comment 1 – NO discussion on extent of remaining grassland in Victoria and Impact of removal on remaining extent: Current estimates calculate that there is less than 1% of the pre-European extent of native grassland remaining in Victoria. Based on this, ALL EPBC applications should quantify their proposed NTGVVP removal impacts against this figure. If the NTGVVP within this site that is proposed for removal- what percentage of the total native grassland remaining does this actually mean? Without quantifiable data, any proposed NTGVVP removal is just a figure, it cannot be meaningfully applied to the extent that is actually remaining. The proposed removal of NTGVVP does not address Point E of the Additional Information as per the DCCEEW request- NO analysis of local and regional scale impacts on the fast-dwindling remaining NTGVVP within Victoria is provided. | Further discussion included noting the percentage of NTGVVP remaining and it's significance relative to the quantity of NTGVVP proposed for removal at this site. | Yes - Section 4.4.1
47 | Brimbank City Council | SLL | Comment 2 – NO discussion on SLL landscape connectivity: Once again, the EPBC RFI documentation does not address the Cairnlea/St Albans SLL meta-population and the role the northern portion of 103 Reid Street provides in maintaining this connectivity. The proposal is for the full removal/development of this site- a development scenario that would be drastic southern section of the Cairnlea/St Albans SLL meta-population. Full development of the site would remove any potential to maintain and enhance SLL connectivity along the Jones Creek corridor, and it would effectively isolate the sites (Denton Grasslands and rail corridor) at the south-eastern end of the corridor. It would also reduce the area available for the SLL meta-population. The proposed loss of SLL habitat does not address Point E of the Additional Information as per the DCCEEW request- NO analysis of local and regional scale impacts on the dwindling supply of remaining SLL habitat within Victoria is provided. | The PD has been updated to include further discussion and review of broader impacts to the partially connected system of grasslands and resident flora and fauna, including the SLL meta-population. A 30 metre setback has now been applied to Jones Creek, avoiding impacts to 1.07ha of SLL habitat and 0.08ha of NTGVVP. | Yes - Section 3.3.3, 4.4.3
48 | Brimbank City Council | SLL | Comment 3- Direct SLL Losses and Research Opportunities: Brimbank Env Dept does not support the current DEECA ‘line’ with regards to the feasibility of mitigation translocations for the Striped Legless Lizard. Brimbank Env Dept has successfully salvage and translocated SLLs from a development site to one of our conservation reserves (Paramount Grasslands). We have data that shows that the translocated SLLs have moved from their release sites and have mixed with the resident SLL population (there has been inter-breeding between resident and translocated SLLs). Whilst Brimbank Env Dept is in complete agreement with DEECA/the experts that SLL habitat should be secured, conserved and managed; this sentiment unfortunately disregards the political and development reality that is on-going in western Melbourne. No matter what the ‘science’ and figures tell us- native grassland and threatened species habitat loss is on-going, which is resulting in the on-going loss of our biodiversity values. This project provides the opportunity for SLL salvage and translocation for scientific and research purposes, and this opportunity should be undertaken to obtain more detailed information on the issues detailed within the document that are considered problematic with regards to SLL salvage and translocation: the high levels of uncertainty regarding the effectiveness of salvage and translocation in the Melbourne Urban Growth Area, species knowledge gaps, and the concern around the habitat quality and conditions of sites selected. Brimbank has suitable translocation sites, which can be utilised for research purposes; if undertaken in strict scientific parameters with the appropriate levels of funding and on-going monitoring. | The effectiveness of salvage and translocation for Striped Legless Lizard has been investigated as recommended in the species National Recovery Plan (O’Shea 2013); seven fundamental criteria for selecting a suitable recipient site are outlined, and it was recommended that translocated populations have a minimum of 75 individuals and are translocated to a site of at least 35 hectares of grassland habitat with no Striped Legless Lizard populations within one kilometre. A total of 16 SLL has been recorded during a single survey season within the Development Site; considering the species can be cryptic and difficult to observe, and their tendency to be trap shy, it is possible that the Striped Legless Lizard population is large enough to provide sufficient specimens to establish a new population in the local area. In situ management for Striped Legless Lizard is always the preferred approach for the conservation of the species, and salvage and relocation of Striped Legless Lizard is not a suitable compensation or in any way mitigates the loss of habitat for the species (DSE 2010; Clemann et. al. 2025). Regardless, providing a suitable recipient site that meets the seven fundamental criteria (O’Shea 2023) is identified, it is recommended that a Salvage and Translocation Plan for any Striped Legless Lizard individuals, or other threatened reptiles such as Tussock Skink Pseudemoia pagenstecheri, encountered during the early earthworks within the Development Site is prepared to reduce the mortality of Striped Legless Lizard directly related to the development. A Salvage and Translocation Plan would be prepared in consultation with a herpetologist with extensive experience and understanding of the ecology of Striped Legless Lizard. While this does not mitigate the loss of important grassland habitat, it may provide a research opportunity to fill in knowledge gaps of the species and establish a new Striped Legless Lizard population in a suitable location. | Yes - Section 4.3.3, 6.1.1
49 | Brimbank City Council | SLL | Section 5 – EPBC RFI Issue 4: Environmental Outcomes. There has been a paucity of information provided in the document with regards to the SLL meta-population on the Cairnlea/St Albans area and the position of the site with regards to the connectivity for the SLL meta-population along the Jones Creek corridor. Therefore, the brief outline/list of MNES to be retained provided above, does not indicate the true scale of impacts that the proposed development in the northern portion of 103 Reid Street will have on local biodiversity/MNES and habitat connectivity. | The PD has been updated to include further discussion and review of broader impacts to the partially connected system of grasslands and resident flora and fauna, including the SLL meta-population. | Yes - Section 3.3.3, 4.4.3
50 | Brimbank City Council | SLL | Section 6 – EPBC RFI Issue 5: Proposed Avoidance, Management and Mitigation Measures. Comment 1- Impacts to SLL meta-population not addressed Whilst the Brimbank Env Dept is supportive of the on-site offset proposed for the southern portion of 103 Reid Street, the proposal does not consider the MNES connectivity impacts associated with the northern portion of 103 Reid Street. The proposed complete development of the northern portion of 103 Reid Street will have on-going impacts to habitat connectivity and the Cairnlea/St Albans SLL meta-population that have not been acknowledged or addressed. | The PD has been updated to include further discussion and review of broader impacts to the partially connected system of grasslands and resident flora and fauna, including the SLL meta-population. A 30 metre setback has now been applied to Jones Creek, avoiding impacts to 1.07ha of SLL habitat and 0.08ha of NTGVVP. | Yes - Section 3.3.3, 4.4.3
51 | Brimbank City Council | Subdivision layout | Comment 2- Unacceptable Subdivision layout compounding destruction of habitat connectivity along the Jones Creek corridor The DRAFT subdivision layout provided on page 10 of the Appendix 1 document (Part 103 Reid Street, Ardeer Economic benefit of proposed rezoning; Deep End Services, 20/11/2020), is copied below. From a biodiversity perspective, this draft layout depicts that the proposed development: Is not setback 30m from the Jones Creek ‘top of the bank’ as required under Clause 14.02 of the Brimbank Planning Scheme. There is no provision of open space, and There is no retention of MNES Values/MNES habitat to retain habitat connectivity along the Jones Creek corridor. The poor subdivision layout that does not address Planning Scheme requirements with regards to waterways and open space, further compounds the elimination of habitat connectivity opportunities along the Jones Creek corridor. | This is a Council and/or State planning issue. Not relevant to this documentation and Commonwealth assessment. A 30 metre setback has now been applied to Jones Creek, avoiding impacts to 1.07ha of SLL habitat and 0.08ha of NTGVVP. | Yes - throughout
52 | Brimbank City Council | Jones Creek Corridor | The current Jones creek corridor adjacent to the site is approx. 27m wide, and the terrestrial land available on the southern side of the creek is approximately 7.5m wide. These widths do not provide the area required for creek corridor management/maintenance access and habitat connectivity. Area within the northern side of the northern portion of 103 Reid Street will be required to ensure habitat connectivity for MNES and the SLL Cairnlea/St Albans meta-population can be retained. | A 30 metre setback has now been applied to Jones Creek, avoiding impacts to 1.07ha of SLL habitat and 0.08ha of NTGVVP. | Yes - throughout
53 | Brimbank City Council | SLL / Jones Creek Corridor | Comment 3- Brimbank Env Dept proposed Jones Creek SLL Habitat Corridor: The SLL habitat corridor proposed by the Brimbank Env Dept for Jones Creek is provided below. This corridor allows for the retention of more MNES values than those accounted for within the RFI documentation. | A 30 metre setback has now been applied to Jones Creek, avoiding impacts to 1.07ha of SLL habitat and 0.08ha of NTGVVP. | Yes - throughout
54 | Brimbank City Council | Remediation | Comment 4- Remediation permit Approval (P0309/2023) and Creek Corridor: Whilst commenting on the remediation permit is outside of the scope of this response, as the MNES impacts from the proposed remediation works were too minor to be referred under the EPBC Act; Brimbank Env Dept did provide comments and permit conditions for this application, which we considered to be a premature application and which we did not support. As a permit application is assessed on the information applicable to that application, a temporary remediation truck access route was allowed under the permit for the remediation works. Whilst it could be argued this route impacts connectivity opportunities along the Jones Creek corridor, the route was temporary and for truck access only- there was to be no earthworks along the truck route and there would be no impediments from the truck movements to rehabilitating and re-seeding/planting the truck access route. | N/A - remediation permit not part of current application / proposed action. | No.
55 | Brimbank City Council | Offsets / SLL / Jones Creek Corridor | Section 7 – EPBC RFI Issue 6: Proposed Offsets: Comment 1- Impacts to SLL meta-population not addressed. Once again, as the documentation has not addressed the Cairnlea/St Albans SLL meta-population and the loss of habitat connectivity along the Jones Creek corridor associated with the complete development of the northern portion of 103 Reid Street; there is an entire major on-going residual impact to MNES that the referral documents have not addressed. Therefore, the offsets that are proposed within the document, are not satisfactory and they do not address all of the MNES impacts associated with the EPBC Act referral. | The PD has been updated to include further discussion and review of broader impacts to the partially connected system of grasslands and resident flora and fauna, including in relation to the SLL meta-population and any offsets implications / changes. A 30 metre setback has now been applied to Jones Creek, avoiding impacts to 1.07ha of SLL habitat and 0.08ha of NTGVVP. | Yes - Section 3.3.3, 4.4.3
56 | Brimbank City Council | Mapping / Onsite Offsets | Comment 2- Southern Portion of 103 Reid Street and s173 Agreement requirements Scrutiny of Figures 2a and 2b reveal inconsistencies between the subject site as indicated in the document’s introduction; inconsistencies with regards to the extent of MNES, the proposed MNES impacts and on-site offsets. Figure 2b has been copied below. As depicted in the bottom left corner of the figure, the study site covers the entire 103 Reid Street southern land parcel, however MNES are only displayed for the portion of the site within the yellow boxed area. Where is the ecological values data for the eastern portion of the land parcel? Why has this data not been provided? What is proposed for this portion of the land parcel? Coincidentally, this ‘missed data’ area of the site covers some of the s173 agreement area. | Mapping updates undertaken to clarify the extent of the development site and on-site offset site. There appears to be some confusion that southern portion of 103 Reid Street (i.e. southern site) is proposed to be impacted. This is not the case. The PD notes throughout that the Southern Site is proposed for on-site offsets (see Section 6.1.1; Figure 2a; Figure 2b), while the Northern Site is proposed to be developed as part of the proposed action. The PD has been updated to further clarify that the portion of 103 Reid Street south of the freeway is proposed to contain an on-site offset site and will not be impacted as part of the proposed action. | Yes - Figure 2a, 2b
57 | Brimbank City Council | Section 173 | As outlined in the s173 agreement, any future development proposal for the affected area of the southern portion of 103 Reid Street must be based on the pre-illegal native vegetation clearance state of the site as detailed in report no. 0938.3 titles: “Flora and Fauna Assessment report on land at 103 Reid Street, Ardeer, Victoria”, by Abzeco Pty Ltd; date September 2009. The map of the native vegetation ‘state’ of the affected area of the site from the 2009 Abzeco report is copied below. The back line through the site indicates the approximate boundary of the southern portion of 103 Reid Street as depicted in Figure 2b. It is apparent, that approximately one hectare of NTGVVP and between 1-1.5ha of SLL habitat are not accounted for the current documentation. There is no discussion of this area in the documentation, and why it has been omitted; even though it is part of the site as described in the document’s introduction. | Mapping updates undertaken to clarify the extent of the development site and on-site offset site. There appears to be some confusion that southern portion of 103 Reid Street (i.e. southern site) is proposed to be impacted. This is not the case. The PD notes throughout that the Southern Site is proposed for on-site offsets (see Section 6.1.1; Figure 2a; Figure 2b), while the Northern Site is proposed to be developed as part of the proposed action. The PD has been updated to further clarify that the portion of 103 Reid Street south of the freeway is proposed to contain an on-site offset site and will not be impacted as part of the proposed action. | Yes - Figure 2a, 2b
58 | Brimbank City Council | Offsets | Comment 3 – Offset Management Strategies and/or Plans As there is omitted/missing information from the application, the Brimbank Env Dept has not reviewed any of the on-site or off-site offset information or strategies/management plans associated with the project. The Brimbank Env Dept retains the right to review and provide comment on these documents once the omitted/missed project information is incorporated/addressed within the RFI documentation. | N/A. The PD contained sufficient information to undertake a review of the OMP and supporting documents. | No.
59 | Brimbank City Council | Section 173 | Section 7.3 – EPBC RFI Issue 6: Offset Management Strategy Comment 1- Removal of the s173 agreement It is not at all clear how the s173 agreement is not associated with the current proposal and how it can be removed. The section of 103 Reid Steet subject to the s173 agreement is copied below. For ease of comparison, we have applied the ‘affected area’ line to the most recent site map provided in Figure 2b of the documentation. From these two images it is clear that a portion of the s173 agreement ‘affected area’ is associated with the current proposal. It is not clear how the s173 agreement can be removed. There is still approx. 1.5ha of the eastern portion of the southern 1013 Reid Street parcel that has been omitted from the documentation, and this land has MNES values which have not been accounted for. | Section 173 is not proposed to be removed. There appears to be some confusion that the southern portion of 103 Reid Street (i.e. southern site) is proposed to be impacted. This is not the case. The PD notes throughout that the Southern Site is proposed for on-site offsets (see Section 6.1.1; Figure 2a; Figure 2b), while the Northern Site is proposed to be developed as part of the proposed action. The PD has been updated to further clarify that the portion of 103 Reid Street south of the freeway is proposed to contain an on-site offset site and will not be impacted as part of the proposed action. | Yes - Figure 2a, 2b
60 | Brimbank City Council | Section 173 | Section 9 – EPBC RFI Issue 8: Environmental Record of Persons Proposing to take the Action Comment 1- Clarity regarding the s173 agreement Whilst a portion of the ‘affected area’ is incorporated into the proposed on-site offset zone- there is still an approx. 1.5ha portion of the ‘affected area’ that is ‘missing’ from the application. This ‘missing area’ contains approx. 1ha of MNES values (based on the 2009 data) that has not been mapped. Mapping from a 2016 report (Ecology and Heritage Partners) depicts that there is still native vegetation within the ‘missing’ portion and that this vegetation meet the criteria to be considered a patch of NTGVVP. This mapping is copied below, with the red polygon indicating the ‘missing’ area from the EPBC RFI document. | Mapping updates undertaken to clarify the extent of the development site and on-site offset site. | Yes - Figure 2a, 2b
61 | Brimbank City Council | Rezoning | Section 10 – EPBC RFI Issue 9: Other Approvals and Conditions: Comment 1- Rezoning application The Brimbank Env Dept has clarified with the Planning department, and the re-zoning application is currently inactive. After the applicants submitted the re-zoning application in 2021, they were provided with a Request for Further Information as the application was incomplete. This information has not yet been provided by the applicant. Some of the items that were incomplete and that required further information, included: Access as the site is currently ‘land locked’ Provision of open space (there is none in the current layout plan) Information about proposed housing densities Land contamination investigations Land use buffers from a former landfill site, located along the western perimeter of the site Water sensitive urban design Biodiversity/native vegetation issues. | This is a Council and/or State planning issue. Not relevant to this documentation and Commonwealth assessment. | No.
62 | Brimbank City Council | VGED | No VGED surveys have been undertaken, despite the site being included in the VGED Habitat Distribution map. There is no mention of VGEDs within the report. | See response to Comment #10